## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Initiation: Requirement gathering, Architecture design, and Tech stack finalization (Spring Boot, React, MySQL). | MUST HAVE | Lucid Chart | Suma Gatti | 3- Completed
S1 | S1 | US-001 | Environment Setup: Setting up Development Environment, Database Schema design, and establishing JDBC connection. | MUST HAVE | MySQL Workbench, IntelliJ IDEA | Suma Gatti | 3- Completed
S2 | S2 | US-001 | Core Backend Development: Implementing Transaction Model and a 'Transaction Generator' to simulate live banking data. | MUST HAVE | Spring Boot Starter Data JPA | Suma Gatti | 3- Completed
S2 | S2 | US-001 | Fraud Engine Logic: Implementing Rule-based detection logic (e.g., amount threshold, frequency checks) and Risk Scoring. | MUST HAVE | Java JDK 17, IntelliJ IDEA | Suma Gatti | 3- Completed
S3 | S3 | US-001 | ML Integration & Insights: Integrating the ML Model, dataset processing, and creating the ML Insights Panel for predictions. | SHOULD HAVE | Python, Google Colab | Suma Gatti | 3- Completed
S3 | S3 | US-001 | Security & Auth: Implementing Role-Based Access Control (Admin/Analyst) and 2FA (OTP via Email) using JavaMailSender. | MUST HAVE | Gmail SMTP | Suma Gatti | 2- In Progress
S4 | S4 | US-001 | Frontend Dashboard: Developing React UI, KPI cards, real-time Monitoring feed, and Data Masking for Analyst role. | MUST HAVE | VS Code, React, Axios | Suma Gatti | 3- Completed
S4 | S4 | US-001 | System Monitoring & Testing: Implementing API Activity logs, Audit logs, System Health status, and Final Deployment. | SHOULD HAVE | Postman, Render, Vercel | Suma Gatti | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 66.5 | 13 | 13 | 15 | 8.5 | 6 | 8.5 | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Finalizing System Architecture & Tech Stack. | 2026-02-04 | 2026-02-06 | Meenakshi, Ramya, Mahima, Ashraf | Design | 3- Completed | 4 | Day 1: 1; Day 2: 2; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0
US-001 | 2 | Environment Setup: Installing JDK, dependencies, IntelliJ & VS Code. | 2026-02-07 | 2026-02-08 | Meenakshi, Ramya, Mahima, Ashraf | Others | 3- Completed | 3 | Day 1: 2; Day 2: 1; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0
US-001 | 3 | Architecture & DB: Creating 'frauddb' and Designing Flow Diagram. | 2026-02-09 | 2026-02-11 | Meenakshi, Ramya, Mahima, Ashraf | Design | 3- Completed | 5 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0
US-001 | 4 | Backend Connectivity: Setting up JDBC & Hibernate configurations. | 2026-02-12 | 2026-02-15 | Meenakshi, Ramya, Mahima, Ashraf | DB | 3- Completed | 4 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0
US-001 | 5 | Data Generation: Developing Transaction Generator logic in Java. | 2026-02-17 | 2026-02-21 | Meenakshi, Ramya, Mahima, Ashraf | Coding | 3- Completed | 6 | Day 1: 0; Day 2: 1; Day 3: 1; Day 4: 0.5; Day 5: 2; Day 6: 1.5; Day 7: 0; Day 8: 0
US-001 | 6 | Fraud Engine: Coding logic/conditions for calculating Risk Scores. | 2026-02-22 | 2026-02-26 | Meenakshi, Ramya, Mahima, Ashraf | Coding | 3- Completed | 4.5 | Day 1: 0.5; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 0; Day 7: 0; Day 8: 0
US-001 | 7 | ML Research: Searching datasets & fixing Accuracy Confusion Matrix. | 2026-02-27 | 2026-04-05 | Meenakshi, Ramya, Mahima | Others | 3- Completed | 10 | Day 1: 1; Day 2: 1; Day 3: 0; Day 4: 1; Day 5: 2; Day 6: 3; Day 7: 1; Day 8: 1
US-001 | 8 | Frontend UI: Developing Dashboard features & KPI cards in React. | 2026-03-05 | 2026-03-12 | Meenakshi | Build | 3- Completed | 12 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 3; Day 5: 1; Day 6: 2.5; Day 7: 0; Day 8: 0.5
US-001 | 9 | Integration: Connecting React frontend with Spring Boot APIs. | 2026-03-11 | 2026-03-14 | Ramya | Coding | 3- Completed | 6 | Day 1: 2; Day 2: 1; Day 3: 2; Day 4: 1; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0
US-001 | 10 | Implementing Email Alerts using SMTP/JavaMail. | 2026-03-15 | 2026-03-16 | Mahima | Coding | 3- Completed | 3 | Day 1: 1; Day 2: 0; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0
US-001 | 11 | Data Privacy: Implementing Data Masking and access for Analyst roles. | 2026-03-17 | 2026-03-19 | Meenakshi | Coding | 3- Completed | 5 | Day 1: 2; Day 2: 1; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0; Day 8: 0
US-001 | 12 | Unit & System Testing: Testing login, API & Fraud logic. | 2026-03-20 | 2026-03-26 | Meenakshi, Ramya, Mahima, Ashraf | System Test | 3- Completed | 4 | Day 1: 0.5; Day 2: 0; Day 3: 1; Day 4: 1; Day 5: 0; Day 6: 1.5; Day 7: 0; Day 8: 0
US-001 | 13 | Deployment: Hosting on Render/Vercel & Final Audit. | 2026-03-27 |  | Meenakshi, Ramya, Mahima, Ashraf | Others | 2- In Progress

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Brainstorming on Architecture Flow and deciding the Tech Stack. | Finalized Spring Boot for Backend and React for Frontend.
Sprint 1 | Day 8 | Discussion on specific conditions and formulas to calculate the Fraud Risk Score. | Decided the logic for transaction limits and calculating risk score.
Sprint 2 | Day 15 | Finalizing the project structure | Set up the root directory and initialized the Git repository.
Sprint 2 | Day 19 | Searching for a suitable Fraud Dataset and deciding the UI features for the dashboard. | Finalised the Kaggle dataset
Sprint 3 | Day 22 | Deep dive into Accuracy & Confusion Matrix (fixing confusion in Precision/Recall values). | Standardised the ML evaluation metrics for the fraud engine.
Sprint 3 | Day 28 | Features to include in frontend and Dashboard UI | Completed Frontend with all required components
Sprint 4 | Day 32 | Working on Email Alerts (OTP/2FA) and backend-frontend integration. | Configured JavaMailSender and resolved Axios connection issues.
Sprint 4 | Day 35 | Final review of Data Masking for Analyst roles and end-to-end testing. | Verified that sensitive info is hidden for Analysts and shown for Admiin

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-04-02 | 17/02/2026 | Meenakshi, Ramya, Mahima, Ashraf | Finalizing System Architecture and flow Diagram. | Working without a centralized DB schema. | Daily Stand-ups to track environment setup progress. | Successfully configured MySQL Workbench and JDBC with IntelliJ.
2 | Sprint 2 | 18/02/2026 | 2026-03-03 | Meenakshi, Ramya, Mahima, Ashraf | Developing a dynamic Transaction Generator for testing. | Using static JSON files for transaction simulation. | Code refactoring and implementing rule-based detection. | Built a custom Java-based generator for live monitoring feed.
3 | Sprint 3 | 2026-04-03 | 17/03/2026 | Meenakshi, Ramya, Mahima, Ashraf | Integrating ML models and 2FA Security logic. | Ignoring security headers and data masking needs. | Using Google Colab for dataset training and validation. | Implemented Role-Based Access (RBAC) and 2FA via Email Service.
4 | Sprint 4 | 18/03/2026 | 2026-04-05 | Meenakshi, Ramya, Mahima, Ashraf | Conducting full End-to-End (E2E) system testing. | Delaying frontend-backend integration for UI components. | Collaborative debugging and final UI/UX refinements. | Deployed the backend on Render and the React frontend on Vercel.